## Sheet1
SPRINT 1 PBI | RESPONSIBLE | STATUS | STORY POINT | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | SPRINT 2 PBI | RESPONSIBLE | STATUS | STORY POINT | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7
Locked UI - Designing Main Menu | Development Team | DONE | 5 | [7 empty] | Locked Service - Delete Files Function | Development Team | DONE | 11
Locked UI - Designing Sub Menu | Development Team | DONE | 5 | [7 empty] | Exception handling | Development Team | DONE | 8
Locked Service - List Files Asc Function | Development Team | DONE | 11 | [7 empty] | Debugging | Development Team | DONE | 5
Locked Service - Add Files Function | Development Team | DONE | 11 | [7 empty] | Testing | Development Team | DONE | 5
|  | NOMINAL |  | 32 | 30.1176 | 28.2353 | 26.3529 | 24.4706 | 22.5882 | 20.7059 |  |  | NOMINAL |  | 29 | 27.2941 | 25.5882 | 23.8824 | 22.1765 | 20.4706 | 18.7647
|  | ACTUAL |  | DAY 1: 32; DAY 2: 32; DAY 3: 32 |  |  | ACTUAL |  | 29 | 29 | 29